## ARCH_RULES
Discipline | Clash Avoidance Rule | Rule Presentation Format
Architectural | Priority list among the disciplines (STRC, MEP, ARCH) for each project must be decided during the kickoff meeting. | BIM Management Plan; Must be present in kickoff meeting agenda
Architectural | The Level Of Detail (LOD) matrix must be defined clearly for the discipline. | BIM Management Plan
Architectural | Always lock/pin the site model in place. | Tutorial Module of Clash Avoidance Assistant; Reminder
Architectural | Axes and levels must be pinned and locked as soon as they are created. | Tutorial Module of Clash Avoidance Assistant; Reminder
Architectural | MEP consultants should provide information about how much volume or space is needed between the ceiling and slab. | BIM Management Plan; BIM Coordination Meetings
Architectural | MEP consultants should provide exact dimension regarding the thickness of the ceiling needs for maintenance accessibility. | BIM Management Plan; BIM Coordination Meetings
Architectural | The dimensions provided by MEP consultants must be available to every modeler/designer/technician when they are working on BIM model. | Tutorial Module of Clash Avoidance Assistant
Architectural | The dimensions of the space between ceiling and slab should precisely match the dimensions provided by the MEP consultants. | Error prompt if the dimension is less than recommended
Architectural | The ceiling thickness in the BIM model should precisely match the dimensions provided by the MEP consultants. | Error prompt if the dimension is less than recommended
Architectural | The interior walls must not travel over the ceiling. | Tutorial Module of Clash Avoidance Assistant; Error prompt if the dimension is less than recommended
Architectural | Use of basic walls without material and layer thickness details should be avoided in the BIM model. | Reminder; Error prompt if basic wall is detected
Architectural | For work shared models, the model must be synchronized with the 'Central' model frequently (min. 1 time/hour). | Tutorial Module of Clash Avoidance Assistant; Reminder
Architectural | For every work session during modeling, errors must be resolved as quickly as possible (Most important: Duplicate elements must be deleted). | Tutorial Module of Clash Avoidance Assistant; Reminder

## STRUC_RULES
Discipline | Clash Avoidance Rule | Rule Presentation Format
Structural | Always lock/pin the site model in place. | Tutorial Module of Clash Avoidance Assistant; Reminder
Structural | Axes and levels must be pinned and locked as soon as they are created. | Tutorial Module of Clash Avoidance Assistant; Reminder
Structural | The structural discipline should receive the first iteration LOD 200 model from the architectural discipline before starting their modeling. | BIM Management Plan; BIM Coordination Meetings
Structural | Once the structural discipline has received the LOD 200 architectural model then the MEP discipline should be consulted. | BIM Management Plan; BIM Coordination Meetings
Structural | Structural and MEP consultants should clearly identify the spaces for mechanical elements within the sheer walls, and beams. | BIM Management Plan; BIM Coordination Meetings
Structural | MEP consultant should provide the exact measurements for required duct and shaft openings. | BIM Management Plan; BIM Coordination Meetings
Structural | The duct and shaft openings in the BIM model should precisely match the dimensions provided by the MEP consultants. | Error prompt if the dimension is less than recommended
Structural | For work shared models, the model must be synchronized with the 'Central' model frequently (min. 1 time/hour). | Tutorial Module of Clash Avoidance Assistant; Reminder
Structural | For every work session during modeling, errors must be resolved as quickly as possible (Most important: Duplicate elements must be deleted). | Tutorial Module of Clash Avoidance Assistant; Reminder

## MEP_RULES
Discipline | Clash Avoidance Rule | Rule Presentation Format
MEP | The work hierarchy of the MEP BIM model for each project should be decided in the kick-off meeting. | BIM Management Plan; BIM Coordination Meetings
MEP | Always lock/pin the site model in place. | Tutorial Module of Clash Avoidance Assistant; Reminder
MEP | Axes and levels must be pinned and locked as soon as they are created. | Tutorial Module of Clash Avoidance Assistant; Reminder
MEP | The insulation dimensions between pipes and ducts should be clearly defined and modeled. | Tutorial Module of Clash Avoidance Assistant; Reminder
MEP | The modeled insulation should match the required dimensions precisely. | Error prompt if the dimension is less than recommended
MEP | HVAC, all slopes and fire protection system should be modeled simultaneously with maximum team coordination. | Tutorial Module of Clash Avoidance Assistant; Reminder
MEP | All clearance spaces required for maintenance should be communicated to all team members. | BIM Management Plan; BIM Coordination Meetings; Tutorial Module of Clash Avoidance Assistant
MEP | The first model iteration should be shared with the architecture and structural disciplines. | BIM Management Plan; BIM Coordination Meetings
MEP | The MEP discipline must request and receive the latest ceiling plans from the architectural discipline (via weekly package publication). | BIM Management Plan; BIM Coordination Meetings
MEP | The MEP discipline must do a manual check to ensure that they have the latest positions of all ceiling fixtures. | BIM Management Plan; BIM Coordination Meetings
MEP | For work shared models, the model must be synchronized with the 'Central' model frequently (min. 1 time/hour). | Tutorial Module of Clash Avoidance Assistant; Reminder
MEP | For every work session during modeling, errors must be resolved as quickly as possible (Most important: Duplicate elements must be deleted). | Tutorial Module of Clash Avoidance Assistant; Reminder
MEP | The MEP discipline must do quality checks to ensure all necessary electrical and fire protection components shown in the 2D plan are present within the model. | BIM Management Plan; BIM Coordination Meetings; Tutorial Module of Clash Avoidance Assistant